## Checklist
Face Recognition using Portenta H7
Name, Vorname | Vatsal Mahajan
Matr.-Nr | 7025694
|  |  |  | First examiner: | Prof. Dr. Elmar Wings
Name, Vorname | Manoj Selvaraju
Matr.-Nr | 7025649
Name, Vorname | Vijay Singh
Matr.-Nr | 7025700
Checklist
No. | Topic | done | date
1 | read ProjectManagement/BestPractice.pdf | done | 2024-04-24
2 | fulfill author.xlsx | done | 2024-04-30
3 | Install TeXLive | done | 2024-04-30
4 | install TeXStudio | done | 2024-04-30
5 | install Sumatrapdf | done | 2024-05-03
6 | configure TeXStudio | done | 2024-05-03
7 | test template report | done | 2024-05-10
8 | test template poster | done | 2024-05-10
9 | test template Presentations/template | done | 2024-05-10
10 | install doxygen | done | 2024-05-20
11 | literature research | done | 2024-06-03
12 | presentation "Literature" | done | 2024-06-03
13 | write n introduction | done | 2024-06-03
14 | presentation "Introduction" | done | 2024-06-05
15 | project plan | done | 2024-06-05
16 | fulfill the list "Resulting Objects" | done | 2024-06-10
17 | presentation "Project Plan" | done | 2024-06-14
18 | update project plan | done | 2024-06-14
19 | update the list "Resulting Objects" | done | 2024-06-15
20 | presentation "Project Plan" II | done | 2024-06-19
21 | rename all tex files along the project plan | done | 2024-06-20
22 | delete or add additional TeX or Python projects, e.g. Manual | done | 2024-06-20
23 | update README.md | done | 2024-06-26
24 | update the checklist | done | 2024-06-26
Processing the project
25
26 | upload the project code | done | 2024-09-04
27 | work along the project plan | done | 2024-09-11
28 | update github every day | done | 2024-09-11
Final stage
30 | check: all website as pdf-file? | done | 2025-01-27
31 | check: all pdfs in the folder Documents? | done | 2025-01-27
32 | check: all images okay? | done | 2025-01-28
33 | check spelling | done | 2025-01-29
34 | check: poster? |  | 2025-01-29
35 | print poster
36 | check: GitHub project | done | 2025-01-30
37 | ready minimal one day before deadline | done | 2025-01-30

## Project Plan V1.0 (eng.)
Face Recognition Using Portenta H7
|  | Week of Year | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
|  | Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
SP No. | SP's Title | Duration
1 | Informative activities / literature | 2.5
2 | Writing the Readme | lifetime of project
3 | Monitoring the MyLiterature.bib | lifetime of project
4 | Writing the Literature Review | 1.5
5 | Writing the Introduction | 1.5
6 | Writing the Domain Knowledge (problem and Data) | 1.5
7 | Writing the List of Materials | 1.5
8 | Writing the Hardware Description | 1.5
9 | Writing the Software Description | 1.5
10 | Writing the Data Mining | 2
11 | Given documentation, Improvements, Translation | 2
12 | methodology | 0.5
13 | KDD process | 1.5
14 | Writing the Deployment | 1
15 | Code developmentDocumentation of the code | 6
16 | Submission of the report | 0
17 | Writing the Data description | 1
18 | Writing the Software BoM, requirements.txt and List of Packages, Tools,… | 1
19 | Program Flowchart | 1
20 | an important used Package - description | 1
21 | an important used Package - description | 1
22 | Hardware improvements | 1
23 | Writing the Tests (cade and report) - software | 1
24 | Writing the Tests - Hardware | 1
25 | Documentation developer | 1
26 | Addition to Documentation (Improvement, todo…) | 1
27 | Development Environment | 1
28 | Creating the Poster | 1
29 | Writing the Manual v.2 | 1
30 | Final review of the project | 1
31 | End of the project | 0
Vacation / holidays
Enrolement / Submission
Meetings
x = f(course of study)
Project Plan for Semester Project
First examiner: Prof. Dr. Elmar Wings
project
report
Submission of the report

## Resulting objects
Face Recognition using Portenta H7
Name, Vorname | Vatsal Mahajan
Matr.-Nr | 7025694
|  |  |  | First examiner: | Prof. Dr. Elmar Wings
Name, Vorname | Manoj Selvaraju
Matr.-Nr | 7025649
Name, Vorname | Vijay Singh
Matr.-Nr | 7025700
List of all Resulting Objects
Subtask | Resulting objects | done | date
Literature | List of keywords | done | 2024-04-24
| Brief description of the sources | done | 2024-04-30
| bib file | done | 2024-04-30
| Bibliography in the report | done | 2024-05-03
| pdf documents | done | 2024-05-03
| quality check | done | 2024-05-03
| … | done
Problem Description | Done in the final report ".\report" on the section "1 Introduction" | done | 2024-05-10
Challenges | Done in the final report ".\report" on the section "1 Introduction" | done | 2024-05-20
Solution | Done in the final report ".\report" on the section "1 Introduction" | done | 2024-05-20
Data Type | Done in the final report ".\report" on the section "2 Domain" | done | 2024-05-20
Data acquisition | Done in the final report ".\report" on the section "2 Domain" | done | 2024-06-03
Data Quality and Quantity | Done in the final report ".\report" on the section "2 Domain" | done | 2024-06-03
Algorithms | Done in the final report ".\report" on the section "5. Data Mining: Convolutional Neural" | done | 2024-06-10
Hyperparameters | Done in the final report ".\report" on the section "5.5. Hyperparameters" | done | 2024-06-10
Requirements | Done in the final report ".\report" on the section "5.6. Requirements" | done | 2024-06-10
KDD process | Done in the final report ".\report" on the section "8. Knowledge Discovery in Databases (KDD) Process" | done | 2024-06-15
ML Pipeline | Done in the final report ".\report" on the section 15.4". KDD: Development" |  | 2024-06-15
Data Selection | Done in the final report ".\report" on the section "9. KDD: Development" | done | 2024-08-12
Data Preprocessing | Done in the final report ".\report" on the section15.4.2-15.4.4 ". KDD: Development" | done | 2024-08-13
Data transformation | Done in the final report ".\report" on the section "10.1 . KDD: Development" | done | 2024-08-14
Data mining | Done in the final report ".\report" on the section "10.2 &15.4.5. KDD: Development" | done | 2024-08-19
Evaluation | Done in the final report ".\report" on the section "15.4.6. Evaluation and Verification" | done | 2024-09-13
Validation | Done in the final report ".\report" on the section "15.4.6. Evaluation and Verification" | done | 2024-09-13
Deployment | Done in the final report ".\report" on the section "11. Evaluation and Verification" | done | 2024-10-22
Data Descritption | Done in the final report ".\report" on the section 9 | done | 2024-10-23
Software BOM & requirements.txt | Done in the final report ".\report" on the sectiion 12.2 &12.3 | done | 2024-10-23
Development environment | Done in the final report ".\report" on section 13 | done | 2024-11-11
Programme Flow Chart | Done in the final report ".\report" on section 14 | done | 2024-11-11
project code and doxygen Documentation | Don in "Code\KeywordSpotting | done | 2024-11-12
Documentation Development (tech doc) | Done in the final report ".\report" on section 15 | done | 2024-11-15
Software Tests | Done in the final report ".\report" on section 16 and Code/KeywordSpotting | done | 2024-11-15
Poster | Done in the final report ".\report" done in ".\poster | done | 2025-01-27
TensorFlow package description | Done in the final report ".\report" on section 6 | done | 2024-11-20
Hardware Tests | Done in the final report ".\report" on section 3.4 | done | 2024-11-17
Manual Completion | Done in the manual | done | 2024-11-19
Results | Done in the final report ".\report" on section 17 | done | 2024-12-13
Conclusions | Done in the final report ".\report" on section 18 | done | 2024-12-13
Future Work | Done in the final report ".\report" on section 18.2 | done | 2024-12-15
Project Plan (10credits) in Master Course "Industrial Informatics"